## Slide 1: Introduction to Scheduling
IE 419

## Slide 2: Jobs
pij – processing time of job j on machine i
rj – release date of job j
dj – due date of job j
wj – weight of job j
pij
rj
dj
wj
M1
M2
M3
Sij
Cij
Sij – starting time of job j on machine i
Cij – completion time of job j

## Slide 3: Jobs & Operations
Often jobs are made up of a set of operations
p2j
rj
dj
wj
p0j
p3j
p1j
precedence constraints

## Slide 4: Example: House Building
…
Excavate
Foundations
Floor joists
…
Exterior plumbing
4 wks
2 wks
3 wks
3 wks

## Slide 5: Resources/Machines
Jobs may need resources
  Mixing machine, back-hoe, cement mixer
Maybe multiple similar resources are available and you need to choose one

## Slide 6: House Building Resources
…
Excavate
Foundations
Floor joists
…
Exterior porch
4 wks
2 wks
3 wks
3 wks
Backhoe
Backhoe operator
Dump truck
…
requires
Carpenter

## Slide 7
Definition of Scheduling
Scheduling concerns optimal allocation or assignment of resources, over time, to a set of tasks or activities.
machines Mi, i=1,...,m (ith machine)
jobs Jj, j=1,...,n (jth job)
Schedule may be represented by Gantt charts.
J3
J2
J2
J3
J1
J1
J1
J3
J4
M3
M2
M1
Machine oriented Gantt chart
M1
M2
M2
M1
M3
M3
M2
J1
J2
J3
Job oriented Gantt chart
M1
M1
J4
t
t

## Slide 8
Bicycle Assembly
  3 workers within a team
  each task has its own duration
  precedence constraints
  no preemption
T7
T2
T1
T5
T4
T6
T9
T8
T10
T3
Examples

## Slide 9
T1
T6
T4
T8
T2
T10
T7
T3
7
T9
T5
14
21
39
2
4
6
14
2
5
6
14
21
Task assignment
T7
T2
T1
T5
T4
T6
T9
T8
T10
T3

## Slide 10
T1
T6
T4
T8
T2
T10
T3
7
T9
T5
14
16
34
2
4
6
9
2
9
17
25
Improved task assignment
16
T7
T7
T2
T1
T5
T4
T6
T9
T8
T10
T3

## Slide 11
An optimal task assignment
T1
T6
T4
T8
T2
T10
T3
7
T9
T5
14
32
2
5
7
14
32
24
16
T7
T7
T2
T1
T5
T4
T6
T9
T8
T10
T3

## Slide 12
2. Classroom Assignment
  one day seminar
  14 seminars
  5 rooms
  8:00 - 5:00pm
  no seminars during the lunch hour 12:00 - 1:00pm

## Slide 13
3. Soft Drink Bottling
  single machine
  4 flavors
  each flavor has its own filling time
  cleaning and changeover time between the bottling of successive flavors
  aim: to minimize cycle time, sufficient: to minimize the total changeover time
f1 - f2 - f3 - f4 - f1
2+3+2+50 = 57
f2 - f3 - f4 - f1 - f2
3+2+50+2 = 57
f3 - f4 - f2 - f1 - f3
2+5+6+70 = 83
f4 - f2 - f3 - f1 - f4
4+3+8+50 = 66
f1 - f2 - f4 - f3 - f1
2+4+6+8 = 20
optimal:

## Slide 14: Application areas
Manufacturing, e.g.:
  job shop / flow shop scheduling
  workforce scheduling
  tool scheduling
Services, e.g.:
  Hotel / airline reservation systems
  Hospitals (operating rooms)
Transportation and distribution, e.g.:
  vehicle scheduling, and routing
  railways

## Slide 15: Application areas
Information processing and communications:
  CPU’s, series and parallel computing
  call centers
Time-tabling, e.g.:
  lecture planning at a University
  soccer competition
  flight scheduling
Warehousing, e.g.:
  AGV scheduling, and routing
Maintenance, e.g.:
  scheduling maintenance of a fleet of ships

## Slide 16: Overview of models
Project Scheduling
  precedence constraints
  minimize makespan
  critical tasks can be identified
Job Shop Scheduling

## Slide 17: Overview of models
Job Shop Scheduling
  minimize makespan or no of tardy jobs
  Mostly for make-to-order manufacturing systems
  Also in services
Flexible Manufacturing Systems
  An automated material handling system controls the movement of jobs
  Mostly for mass production systems
  Maximize throughput

## Slide 18: Overview of models
Lot Scheduling
  Switching between products incurs a setup cost
  Minimize total inventory and setup costs
  Process industries, e.g. oil refinery, paper mill
Reservation Systems
  Job start and complete times are fixed
  Decide to process the job or not
  Maximize no. of jobs processed or utilization
  Services, e.g. hotels, car rental agencies.

## Slide 19: Overview of models
Timetabling
  Certain jobs use the same equipment and cannot be processed at the same time
  Minimize makespan
  Examples: repair shops, classroom scheduling
Workforce Scheduling
  Assign personnel to shifts
  Constraints due to equipment requirements and work rules
  Minimize number of employees or total cost